## FY 23 RO 3rd qtr analysis
FY23 R6 Final Timber Volume Sold Target Assignment to Units (Column G), 2-22-23
Forest | FY23 Target (base + carryover) | Base (3+1) | Carryover | Additional capability (in addition to column c) | FY23 Final Target Assignment (MMBF) | Forest estimates from 3+1 meetings | Comments from 3+1 meeting notes
0602 FWI | 67 | 67 | 0 | 5 | 72 | 77.8 | Forest plans to attain 77.8 but may need to adjust in order to meet FY 24 targets. Snow limiting access.
0604 MAL | 60.6 | 45 | 15.6 | 0 | 60.6 | 61.8 | Halo IRSC is (32 mmbf) is at risk due to contracting. Snow limiting access. LCFW project has complications (syline logging systems expensive, but tethered included). Low staffing. Not much contingency.
0605 MBS | 10.9 | 8 | 2.9 | 0 | 10.9 | 10.5 | Need assistance with apprasial. NMFS delays with Humpback TS. Need crushed rock for roads.
0609 OLY | 17.56 | 9.56 | 8 | 0 | 17.56 | 23.7 | Plus up from 18. Setting up for 1st qtr sale in FY 24.
0612 SIU | 40 | 40 | 0 | 5 | 45 | 45 | Complaints about scraficing auatics work for additional 5 mmbf
0616 WAW | 20 | 20 | 0 | 3 | 23 | 23 | Snow limiting access. Moved sale up from FY 24 to make target. NEPA is pinch point moving forward. Understaffed by 11 people. Proactive with sale prep, CE, and ODF.
0617 OKE | 14 | 14 | 0 | 25 | 39 | 47.5 | Comfortable with 47.5 and possible plus up to potentially 61. Snow is limiting access. Twisp EA being litigated. Upper Wenatchee has delays with USFWS.
0618 WIL | 35 | 35 | 0 | 5 | 40 | 40 | Comfortable with 40 and possible plus up (pending). Snow limiting access. IRSC are somewhat risky. Lots of potential litigation.
0621 COL | 105 | 105 | 0 | 0 | 105 | 105 | Possible plus up to 121. Iron TS (12 mmbf) is biggest risk. Potential for litigation. Low staffing issues. FS is retiring in June.
Totals | 370.06 | 343.56 | 26.5 | 43 | 413.06 | 434.3
0601 DES | 20.607 | 20 | 0.607 | 5 | 25.607 | 26 | Snow limiting access. Need better communication about timber targets from Forest leadership. Not much contigency plan.
0606 MTH | 6.8 | 5 | 1.8 | 20 | 26.8 | 27 | Denied alt. crusing method. Balboa TS has lots of pine and if not sold would put them less 50% target.
0610 RRS | 15 | 15 | 0 | 4.5 | 19.5 | 20 | May come up short due extreme staffing shortages and reinitiation of consultation. Tapping into biomass market.
Totals | 67.407 | 65 | 2.407 | 29.5 | 96.907 | 73
0603 GIP | 51.5 | 48 | 3.5 | 0 | 51.5 | 36.1 | Shortage due to NEPA not getting signed (Yellowjacket EA). Working with WDNR. Trying to reduce roads package costs.
0607 OCH | 10 | 10 | 0 | 0 | 10 | 4 | Shortage due to NEPA not getting signed. NEPA is pinch point. Possible plus up in FY24
0614 UMA | 22.5 | 18 | 4.5 | 0 | 22.5 | 18.8 | Carryover sold but coming up short. Staffing shortage. Ellis EIS in limbo. Snow limiting access. Services are restricting tethered logging proposals.
0615 UMP | 25 | 25 | 0 | 0 | 25 | 21.7 | Short but sale scheudle shows shelf stock, but only in prep phase. Need engineering capacity. Litigation delaying NEPA. May have contingency for one additional sale. May not make target.
Totals | 109 | 101 | 8 | 0 | 109 | 80.6
R6 Totals | 521.467 | 484.56 | 36.907 | 72.5 | 593.967 | 587.9 | Tentatively on target for meeting 575 MMBF assigned to R6
Assigned Target to Region from WO = 575 MMBF (2-9-23)

## Sale Schedules
Forest | Sale Name | Contract Type | Volume (MMBF) | Status | Comments
0602 FWI | Solomon IRTC | IRTC | 10562 | Awarded
| Spring Creek Road | IRTC | 480 | Awarded
| Hog | IRSC | 11000
| Anders | IRTC | 18956
| CHI WUI | SPA | 3339
| Kirk | IRTC | 11000
| Chiloquin Ridge | ODF | 3000 | Awarded
| Coleman GNA | ODF | 15800 | Awarded
| Box GNA | ODF | 3672
| Total |  | 77809
0604 MAL | Gem 2400-6 | 2400-6 | 7400 | June
| LCFW 2400-6 | 2400-6 | 3000 | June
| Halo 1 | IRSC | 19400 | Pending | Advertisement to come in June
| Halo 2 | IRSC | 13029 | Pending
| HOGAN 2400-6 | 2400-6 | 500 | June
| Del TS | ? | 16000 | Awarded
| Add Vol. |  | 2500
| Total |  | 61829
0605 MBS | Haller reoffer | Stewardship | 2870 | Awarded
| Upper Green | 2400-6 | 3640 | Awarded
| Pilchuck GNA | GNA | 1500 | 4th
| Rockwood 2 GNA (NEPA:Hanson) | GNA | 500 | ?
| Humpback (NEPA:Hanson) | 2400-6 | 1800 | 4th
| Bolt Creek ROW Salvage | 2400-4 | 200 | 4th
| Total |  | 10510
0609 OLY | Hobbit GNA | GNA | 4500 | Pending
| Captin Hook Re-offer | 2400-6 | 9808 | Awarded
| Griz | 2400-6 | 9564 | 3rd
| Total |  | 23872
0612 SIU | Griff DxP | 2400-6 | 1598 | 1st
| Divide DxP | 2400-6 | 8438 | 3rd
| Deso DxP | 2400-6 | 1269 | 3rd
| Later DxP IRTC | IRTC | 11880 | 4th
| Pawn Dxp IRTC | IRTC | 9966 | 4th
| Legion DxP | 2400-6 | 453 | 4th
| Shank DxP | 2400-6 | 6980 | 4th
| Fuelwood | ? | 4500 | 4th
| Total |  | 45084
0616 WAW | North Mosquito TS (Whit) | 2400-6 | 8822 | 4th
| Pioneer Timber Sale (Lag) | 2400-6 | 1897 | Awarded
| Bull Run TS (Whit) SBA | SBA 2400-6 | 1472 | 3rd
| 5 Points Fuels Reduction (Lag) | ? | 3900 | 4th
| Double Creek Salvage TS | 2400-6 | 1300 | 3rd
| Broady DxP TS (Wmo) | 2400-6 | 2053 | ?
| Sturgill Decks 1 | 2400-4 | 1051 | Awarded
| Sturgill Decks 2 | 2400-4 | 584 | Awarded
| Add. Vol. |  | 2000
| Total |  | 23079
0617 OKE | Twisp "Woodpecker DxP" (MVRD) | 2400-6 | 5300 | Litigation
| Twisp "Lookout STWD DxP" (MVRD) | 2400-6 | 12600 | Awarded
| Upper Wenatchee "Meadow DxP" (WRRD) | 2400-6 | 12800 | ? | Need
| Little Naches Upland (Naches) | Stewardship | 16250 | 3rd
| Taneum (Cle Elum) | 2400-6 | 10600 | 3rd
| Taneum Sale 2 (Cle Elum) | 2400-6 | 1600 | 4th
| "Yellowbelly Firewood Decks TP" (Cle Elum) | 2400-4 | 70 | ?
| "Nugget" (Cle Elum) | ? | 70 | ?
| Cougar Danger Tree - Com. Firewood (ENT) | 2400-4 | 800 | ?
| Added Volume |  | 1000
| Total |  | 61090
0618 WIL | Swamp Deck TP | 2400-4 | 129 | 3rd
| Ridge Deck TP | 2400-4 | 128 | 3rd
| Millie Deck TP | 2400-4 | 500 | 3rd
| Crystal Decks TP SBA | 2400-4 | 750 | 3rd
| Valley Thin | 2400-6 | 5354 | 4th
| LFC SBA | 2400-6 | 1161 | 4th
| Heeler Decks TP SBA | 2400-4 | 4000 | 3rd
| Holiday IRSC | IRSC | 9271 | 3rd
| BB | ? | 4157 | 4th
| Nene | ? | 1482 | 3rd
| PGE Decks | 2400-4 | 100 | 4th
| BCLH IRSC | IRSC | 30727 | 3rd
| PRI IRSC | IRSC | 2714 | 3rd
| GNA Log | GNA | 8000 | 3rd
| Bits GNA | GNA | 1521 | 3rd
| Total |  | 69994 | 3rd
0621 COL | Silver GNA | GNA | 5792 | Awarded
| Sanpoil | ? | 16100 | Awarded
| Ferry Lake CG | 2400-6? | 220 | Awarded
| Iron | IRTC? | 12404 | 3rd
| Spike | IRTC? | 33000 | 3rd
| Kings Lake | IRTC? | 8026 | 4th
| Hart | IRTC? | 15000 | 4th
| McMann | IRTC? | 1000 | 4th
| Drummond | IRTC? | 15000 | 4th
| Mill Creek GNA | GNA | 10000 | 4th
| Add. Vol |  | 5000
| Total |  | 121542
0601 DES | Fish DxP Timber Sale | 2400-6T | 8000 | 4th
| Sage DxP Timber Sale | 2400-6T | 7234 | 3rd
| CC Decks Timber Sale (advertising) | 2400-6T | 1058 | 3rd
| Big DxP IRSC Stew NPL | IRSC | 8846 | 3rd
| SJ Decks Timber Sale (awarded) | 2400-6T | 630 | 2nd?
| FY 2023 Add Vol | Active Contracts | 500
| Total |  | 26268
0606 MTH | Tripod Deck | 2400-4 | 1635 | Awarded
| Devils Ridge Deck | 2400-4 | 255.84 | Awarded
| Pipeline Settlement | 2400-6 | 749.32 | Awarded
| Car GNA Timber Sale | GNA | 9000.004 | 3rd
| Balboa TS | 2400-6 | 15107.56 | 4th
| Dog River Deck | 2400-4 | 166.4 | 4th
| Total |  | 26914.124
0610 RRS | Shan Apple SPA (MOD) | Stewardship | 676.69 | 3rd
| Oak Flat DxP | 2600-6 | 7965 | 4th
| Ragsdale (CHFT) (SBA) | 2600-6 | 3774 | 3rd
| Watertower SPA | 2400-6 | 250 | 4th | May not go this FY. Very low vol
| Flowline (PacifiCorp Direct Settlement Sale) | 2400-6 | 105.263 | 4th
| Atlas TS (Stella) | 2400-6 | 3679.602 | Awarded
| Prestige Topwood (Stella) | 2400-6 | 139 | Awarded
| DAC Topwood (Stella) | 2400-6 | 394 | Awarded
| Slim Prospect GNA (Stella) GNA | GNA | 2413 | Awarded
| Slater Re-open | ? |  | N/A
| Farewell Bend (Stella) | 2400-4 | 250 | 4th
| Union Creek 23 | 2400-4 | 50 | TBD
| Add. Vol |  | 1221
| Total |  | 20917.555
0614 UMA | 1007 Rd Small Sale | 2400-6T | 100
| Lick Salvage | IRTC | 800 | 3rd
| Sunflower | 2400-6 | 1500 | 4th
| Buck Mountain TS | 2400-6 | 5700 | Awarded
| Elbow ODF GNA | GNA | 4200 | 4th
| Crossbow TS | 2400-6 | 4500 | Awarded
| Firewood |  | 1500
| Add. Vol |  | 500
| Total |  | 18800
0615 UMP | Bogus |  |  | Postponed
| Mace Mountain |  | 1000 | 3rd
| Umpqua Roadside IRSC | IRSC | 2500 | 3rd
| L.C. Snow Reoffer Stewardship | Stewardship | 2100 | 4th
| Wolf SBA | 2400-6 | 6000 | 4th
| Calf | ? | 7750 | 4th
| GNA | GNA | 1000 | ?
| Permits |  | 400
| Add-on Vol / Small Sales |  | 1000
| Total |  | 21750
0603 GIP | Ames Stew (FY2022) NEPA: Kraus | Stewardship | 8800 | 4th
| Corn- Stew | Stewardship | 11890 | 4th
| Pop GNA (Middle Wind) | GNA | 1500 | 4th
| Falls Stew(FY2022) NEPA: Middle Wind | Stewardship | 3550 | Awarded
| 10 mile - Stew (Middle Wind) | Stewardship | 7800 | 4th
| Kidd #1-TS/Stew -Yellowjacket | Stewardship |  |  | On hold due to NEPA
| Laser TS -(Yellow Jacket) Pipeline | Stewardship |  |  | On hold due to NEPA
| Horse TS (Pipeline, Nisqually NEPA) -FY23?? | 2400-6 | 500 | ?
| Add on Volume |  | 2000
| Misc Sales |  | 100
| Total |  | 36140
0607 OCH | Peak Timber Sale (Awarded) | 2400-6T | 1960 | Awarded
| Tin Cup Timber Sale | 2400-6T | 1750 | 3rd
| Starry Salvage | 2400-4T | 127 | 3rd
| FY 2023 Add Vol | Active Contracts | 125
| Total |  | 3962
| Total |  | 649560.679